## Cover
CloseClinic
The AI-Powered Sales OS for Contractors
Strategic Launch Package
Date: 2026-04-21
Prepared by Max for Rob Acheson
TABLE OF CONTENTS
# | Sheet | Description
1. | Cover | Title page + TOC
2. | Competitive Kill-Sheet | 12 competitors ranked by GEO score, moats, fatal flaws, attack vectors
3. | White Space Map | 9 market territories — 3 open lanes to own
4. | Pricing Tiers | 3-tier service architecture: Diagnose, Leaky Bucket AI, Fractional VP
5. | 90-Day Execution Plan | Day-by-day execution roadmap, Week 1 through Week 13
6. | 3-Year Financial Projection | Year 1 quarterly + Year 2 + Year 3 forecast with chart
7. | Unit Economics | Per-client COGS for Tier 2 + LTV calculations
8. | Tech Stack | 12-tool AI + orchestration stack with costs
9. | KPI Dashboard | Commercial + Product + GEO metrics tracker
10. | Risk Register | 7 key risks with probability, impact, mitigation
11. | 90-Day Name Shortlist | Top 5 names — CloseClinic recommended

## Competitive Kill-Sheet
12-COMPETITOR KILL-SHEET — GEO / AI Visibility Analysis
Rank | Brand | GEO Score | Owner | Moat | Fatal Flaw | Attack Vector | Citability | Brand Auth | Crawler | Schema | llms.txt | Pricing Transparent (Y/N) | Wikipedia (Y/N)
1 | Hook Agency | 78 | Tim Brown | 156K YT + GEO-literate | Marketing only, no sales training | Partner not compete | 72 | 85 | OK | Strong | Yes | N | N
2 | Contractor Fight | 72 | Tom Reber | 1,091 podcasts + TM'd IP | No Wiki, no Course schema, no #'s | Attack on schema + quantified outcomes | 70 | 82 | OK | Weak | No | N | N
3 | D2D Experts | 64 | Sam Taggart | D2DCon + llms.txt | No Wiki, weak schema | D2DCon owns events — we own AI | 65 | 70 | OK | Weak | Yes | Y | N
4 | STG | 63 | Ryan Groth | llms.txt + AI-open | FAKE 5.0/500 schema VIOLATION | Rob knows every weakness from inside | 60 | 68 | OK | Broken | Yes | N | N
5 | Roofing Insights | 58 | Dmitry Lipinskiy | 147K YT subscribers | No schema, no llms.txt | YT is his — AI search is ours | 55 | 72 | OK | None | No | N | N
6 | Breakthrough Academy | 58 | Canadian team | Contractor Evolution podcast | Systems-only, NO sales lane | Wide open on sales-first positioning | 57 | 65 | OK | Weak | No | N | N
7 | Forrest / FPG | 58 | Jason Forrest | 9 Stevies + 6 books | Not contractor-specific | Vertical depth beats horizontal authority | 56 | 80 | OK | OK | No | N | N
8 | Roofing Academy | 42 | Randy Brothers | 200-episode podcast | Wix junk sitemap, zero schema | Entity-invisible to LLMs | 40 | 55 | Weak | None | No | N | N
9 | Closers.io | 38 | Cole Gordon | Celebrity client logos | NOT home services | Wrong vertical | 45 | 65 | OK | Weak | No | Y | N
10 | TOP REP | 38 | Chuck Thokey | Transparent pricing ($97-$54K) | Entity-invisible | No entity graph presence | 38 | 50 | OK | Weak | No | Y | N
11 | CertainPath | 42 | Lon Cassel | 1,500+ members | Primary domain parked, no schema | Technical neglect | 35 | 60 | Weak | None | No | N | N
12 | Roof Strategist | 35 | Adam Bensman | 117K YT + 660 podcasts | Sitewide noindex,nofollow | Self-inflicted invisibility | 30 | 70 | Blocked | None | No | N | N
Universal patterns: 0/12 have Wikipedia ¦ Only Hook has competent schema ¦ Only 2/12 publish pricing — transparency is a weapon.

## White Space Map
WHITE SPACE MAP — 9 Territories
# | Territory | Current Owner | Open? (Y/N)
1 | Mindset / Community | The Contractor Fight (TCF) | N
2 | YouTube Education | Roofing Insights, Hook Agency | N
3 | Door-to-Door (D2D) Sales | D2D Experts | N
4 | Business Systems | Breakthrough Academy | N
5 | Marketing / Lead Generation | Hook Agency | N
6 | Elite Sales Authority | Forrest Performance Group | N
7 | AI-native Sales OS | NOBODY | Y
8 | 24/7 AI Receptionist (Leaky Bucket) | NOBODY | Y
9 | Done-FOR-you AI + Done-WITH-you Coaching hybrid | NOBODY | Y
All 3 open lanes converge on the same category: 'AI Sales OS for Contractors' — this is what we're building.

## Pricing Tiers
SERVICE ARCHITECTURE — 3 Tiers
Feature / Metric | TIER 1 — DIAGNOSE | TIER 2 — LEAKY BUCKET AI | TIER 3 — FRACTIONAL VP + AI STACK
Tagline | Diagnose the leaks | Install the AI stack | Fractional VP runs it
Price / month | $1,497/mo | $4,997/mo | $14,997/mo
Onboarding Fee | $0 | $5,000 | $15,000
Annual Option | $14,970/yr (save 17%) | Annual billing available | 12-month minimum required
Target Gross Margin | 78-85% | 65-72% | 45-55%
ICP | Contractors $1M-$3M, 2-5 reps | Contractors $3M-$10M, 5-15 reps (PRIMARY) | Contractors $10M-$40M, 15-60 reps
Sales Audit | Leaky Bucket Diagnostic (2wk) | Included + quarterly refresh | Included + monthly refresh
Baseline Playbook | Yes — PVP framework + objection handling | Yes | Yes + custom
Group Coaching | 2x/mo Zoom cohort (max 20) | Included | Included
1:1 Coaching | Not included | Weekly 1:1 virtual with named coach | Weekly 1:1 + Fractional VP onsite 2 days/mo
LMS Access | 50+ on-demand modules | Full library + advanced tracks | Full library + custom tracks
Slack Community | Included | Included (priority channel) | Included (private executive channel)
Monthly Scorecard | KPI tracker | Enhanced scorecard + call review AI | Executive scorecard + owner QBR
AI Voice Receptionist | No | Yes — Synthflow 24/7, multilingual | Yes — Synthflow + ElevenLabs premium
AI Chatbot | No | Yes — Chatbase on client website | Yes — Chatbase + custom LLM agents
Call Review AI | No | Yes — every call scored, weaknesses flagged | Yes + monthly rep coaching reports
SMS/Email Automations | No | Yes — n8n sequences | Yes — custom n8n + custom dashboards
GHL Sub-Account | No | Custom GHL with all workflows | Custom GHL + Close/HubSpot integration
QBR Cadence | Annual review | Quarterly business review | Monthly QBR with owner
In-Person Offsite | No | No | Quarterly 2-day sales team retreat
A-Player Recruiting | No | No | Yes — 2 placements/year included
Rep Hiring System | No | No | Interview scorecards + ramp playbook
Priority Support | Email support | Email + Slack | 24/7 on-call Slack + phone
YEAR 2 REVENUE MIX TARGET
% of Clients | 30% | 55% | 15%
% of Revenue | 12% | 58% | 30%
Blended ARPU |  | ~$5,800/mo (blended across all tiers)
Blended GM |  | ~68%

## 90-Day Execution Plan
90-DAY EXECUTION PLAN — Day by Day
Day | Week | Phase | Task | Owner | Deliverable | Dependency | Status
1 | Week 1 | Foundation Lock | Lock brand name: CloseClinic. Register .com + .ai + .co domains | Rob | Domains registered | —
1 | Week 1 | Foundation Lock | File LLC (Texas or Delaware) via Stripe Atlas or Clerky | Rob | EIN pending | —
1 | Week 1 | Foundation Lock | Open Mercury or Brex business bank account | Rob | Account funded | LLC filed
2 | Week 1 | Foundation Lock | Sign Synthflow agency plan + Chatbase agency plan | Rob | Credentials live | Bank account
2 | Week 1 | Foundation Lock | Spin up n8n on Hetzner VPS | Max | n8n URL live | —
2 | Week 1 | Foundation Lock | Register Twilio account, begin A2P 10DLC registration | Max | Twilio account created | LLC filed
3 | Week 1 | Foundation Lock | Hire brand designer (Fiverr Pro / Contra) — logo, wordmark, palette | Rob | Logo brief sent | Name locked
3 | Week 1 | Foundation Lock | Resignation letter to STG (clean, professional, 2 weeks notice) | Rob | Letter sent | —
4 | Week 1 | Foundation Lock | USPTO trademark application (CloseClinic wordmark + design) | Rob | TM filing submitted | Logo draft
4 | Week 1 | Foundation Lock | Set up Google Workspace @closeclinic.com | Rob | Email live | Domain registered
5 | Week 1 | Foundation Lock | Draft Founder's Letter announcement (LinkedIn + email list) | Max | Draft ready | —
5 | Week 1 | Foundation Lock | Schedule brand photos + video reel (Dallas) | Rob | Session booked | —
6 | Week 1 | Foundation Lock | Build master Synthflow voice agent template (roofing-flavored) | Max + Rob | Template live | Synthflow account
6 | Week 1 | Foundation Lock | Build master Chatbase chat agent template | Max + Rob | Template live | Chatbase account
7 | Week 1 | Foundation Lock | WEEK 1 RETRO + ship first internal demo to 3 friendlies | Rob + Max | 3 demos completed | Templates live
8 | Week 2 | Website & Core Assets | Scaffold Next.js 16 project on Vercel | Max | Repo + prod URL live | Domain
9 | Week 2 | Website & Core Assets | Ship /home, /about, /services, /pricing, /contact pages | Max | 5 pages live | Scaffold
9 | Week 2 | Website & Core Assets | Draft and review homepage hero + value props copy | Rob + Max | Hero copy approved | Positioning locked
10 | Week 2 | Website & Core Assets | Embed Organization + Person + LocalBusiness + Service + FAQPage + Course JSON-LD on all pages | Max | Schema validates on Rich Results Test | Pages shipped
10 | Week 2 | Website & Core Assets | Publish pricing page with all 3 tiers (transparent pricing) | Max | /pricing live | Schema ready
11 | Week 2 | Website & Core Assets | Write + publish llms.txt + llms-full.txt + ai.txt + ai.toon | Max | Files live at root | Website live
11 | Week 2 | Website & Core Assets | Submit sitemap to GSC, Bing Webmaster Tools, IndexNow | Max | Submitted + verified | Website live
12 | Week 2 | Website & Core Assets | Ship interactive Leaky Bucket Diagnostic lead magnet (React scorecard) | Max | Live on /diagnostic | Website live
12 | Week 2 | Website & Core Assets | Embed demo AI receptionist on homepage ('Call our AI right now') | Max | Demo phone line live | Synthflow template
13 | Week 2 | Website & Core Assets | Write 10 foundational blog posts (FAQ-seeded, GEO-optimized) | Max drafts, Rob approves | 10 posts published | Website live
13 | Week 2 | Website & Core Assets | Ship comparison pages: CloseClinic vs STG, vs Contractor Fight | Max | 2 comparison pages live | Positioning
14 | Week 2 | Website & Core Assets | WEEK 2 RETRO + soft-launch to personal network | Rob | Soft launch email sent | Website live
15 | Week 3 | Authority Build | Publish founder's letter on LinkedIn (announce CloseClinic) | Rob | Post live | Letter drafted
15 | Week 3 | Authority Build | Announcement email to personal Rolodex (500+ contractor contacts) | Rob | Email sent | Email list
16 | Week 3 | Authority Build | Record first 5 podcast episodes — CloseClinic Diagnostic Podcast | Rob | 5 episodes recorded | Podcast setup
17 | Week 3 | Authority Build | Publish Episode 1 on YouTube + Spotify + Apple Podcasts | Max | Ep 1 live on 3 platforms | Recording
17 | Week 3 | Authority Build | Configure podcast RSS + submit to Apple/Spotify/Google | Max | RSS feed verified | Ep 1 ready
18 | Week 3 | Authority Build | Seed 10 Reddit answers (r/Roofing, r/HVAC, r/RoofingSales, r/Construction) | Rob | 10 answers posted | Reddit account
19 | Week 3 | Authority Build | Pitch Roofing Contractor Magazine for feature ('Ex-STG VP launches AI OS') | Max writes, Rob sends | Pitch sent | Press materials
20 | Week 3 | Authority Build | Pitch Pro Remodeler, Qualified Remodeler, ProSales for bylined articles | Rob | 3 pitches sent | Bio + samples
20 | Week 3 | Authority Build | Create media kit PDF with positioning, bio, headshots, logos | Max | Media kit PDF live | Brand photos
21 | Week 3 | Authority Build | WEEK 3 RETRO — confirm 2 content pillars live (podcast + blog) | Rob | Retro completed | Content shipped
22 | Week 4 | First Paid Clients | Convert 3 friendlies to Tier 2 @ $3,497/mo founding price (12mo) | Rob | 3 contracts signed | Demos done
23 | Week 4 | First Paid Clients | Onboard Client #1: Synthflow + GHL sub-account + n8n + Chatbase | Max | Client #1 live | Contract
24 | Week 4 | First Paid Clients | Onboard Client #2 (full stack setup) | Max | Client #2 live | Contract
25 | Week 4 | First Paid Clients | Onboard Client #3 (full stack setup) | Max | Client #3 live | Contract
26 | Week 4 | First Paid Clients | Capture baseline metrics for case study (before-state data) | Rob | Baseline data captured | 3 clients live
27 | Week 4 | First Paid Clients | Soft-launch Tier 1 ($1,497/mo) to broader email list | Rob | 5 T1 leads generated | Email list
28 | Week 4 | First Paid Clients | Convert 2 Tier 1 founding members | Rob | 2 T1 contracts signed | Leads qualified
29 | Week 4 | First Paid Clients | MONTH 1 CLOSE: 5 paying clients, ~$17K MRR, website + podcast live | Rob | Milestone achieved | All prior tasks
30 | Week 4 | First Paid Clients | Record 'How I left STG and built $17K MRR in 30 days' LinkedIn post | Rob + Max | Post live | Milestone hit
31 | Week 5 | Authority & Scale | Launch weekly Leaky Bucket Live webinar (Thursday 1pm CT) | Rob + Max | Webinar #1 live | Zoom + registration page
32 | Week 5 | Authority & Scale | Guest podcast #1: The Roofer Show | Rob | Episode recorded | Pitch accepted
33 | Week 5 | Authority & Scale | Guest podcast #2: Start Build Grow | Rob | Episode recorded | Pitch accepted
34 | Week 5 | Authority & Scale | Publish 5 more foundational blog posts (FAQ pages) | Max | 5 posts live | Content calendar
35 | Week 5 | Authority & Scale | Outreach to 50 warm contacts for discovery calls | Rob | 50 emails sent | CRM
36 | Week 5 | Authority & Scale | Weekly webinar #2 — push recording to YouTube | Rob + Max | Webinar live + YT upload | Webinar #1
37 | Week 5 | Authority & Scale | Week 5 retro — pipeline review + KPI update | Rob | Retro notes | —
38 | Week 6 | Authority & Scale | Kick off State of Contractor Sales 2026 research (n=500) | Max | Survey live | Partnership
39 | Week 6 | Authority & Scale | Guest podcast #3: D2D Podcast (Sam Taggart's show) | Rob | Episode recorded | Pitch
40 | Week 6 | Authority & Scale | Close 3 new Tier 2 clients (pipeline from webinars) | Rob | 3 contracts signed | Pipeline
41 | Week 6 | Authority & Scale | Onboard 3 new clients (week-of-signing) | Max | 3 clients live | Contracts
42 | Week 6 | Authority & Scale | Ship case study #1: first client's inbound answer rate delta | Max | Case study PDF + page | Baseline + 30 days
43 | Week 6 | Authority & Scale | Submit speaking applications: IRE 2027, Win the Storm | Rob | Applications submitted | Speaker bio
44 | Week 6 | Authority & Scale | Week 6 retro | Rob | Retro notes | —
45 | Week 7 | Authority & Scale | Publish comparison page: CloseClinic vs Roofing Insights | Max | Page live | Competitive research
46 | Week 7 | Authority & Scale | Weekly webinar #3 | Rob | Webinar live | —
47 | Week 7 | Authority & Scale | Guest podcast #4: Contractor Evolution (BTA) | Rob | Episode recorded | Pitch
48 | Week 7 | Authority & Scale | Close 3 more Tier 2 clients | Rob | 3 contracts signed | Pipeline
49 | Week 7 | Authority & Scale | Onboard 3 more clients | Max | 3 clients live | Contracts
50 | Week 7 | Authority & Scale | Ship Success Stories page with 3 early wins + metrics | Max | Page live | Case studies
51 | Week 7 | Authority & Scale | Week 7 retro — GEO audit checkpoint | Max | GEO report | —
52 | Week 8 | Authority & Scale | Publish 10 additional blog posts (scale GEO footprint) | Max | 10 posts live | Content calendar
53 | Week 8 | Authority & Scale | Guest podcast #5: Roofing Success | Rob | Episode recorded | Pitch
54 | Week 8 | Authority & Scale | Close 4 more clients (reach 15 active by Day 60) | Rob | 4 contracts signed | Pipeline
55 | Week 8 | Authority & Scale | Onboard 4 new clients | Max | 4 clients live | Contracts
56 | Week 8 | Authority & Scale | Hire first FTE: Head of Delivery (certified sales trainer) | Rob | Offer extended | $50K MRR
57 | Week 8 | Authority & Scale | Publish Guest Podcast #6: Limitless CEO | Rob | Episode live | —
58 | Week 8 | Authority & Scale | Publish State of Contractor Sales 2026 report (preview) | Max | Report PDF + landing page | Survey data
59 | Week 8 | Authority & Scale | Weekly webinar #4 + 30-day check-ins for first clients | Rob | Retention pass complete | —
60 | Week 8 | Authority & Scale | DAY 60 MILESTONE: 15 clients, ~$60K MRR, Head of Delivery hired | Rob | Milestone achieved | All prior
61 | Week 9 | Dominate Category | Publish book proposal; pitch Lioncrest/Scribe/Forbes Books | Rob | Proposal sent to 3 publishers | Content library
62 | Week 9 | Dominate Category | Launch affiliate program for existing contractor consultants | Max | Affiliate portal live | Ops
63 | Week 9 | Dominate Category | Close 3 more Tier 2 + 1 Tier 3 client | Rob | 4 contracts signed | Pipeline
64 | Week 9 | Dominate Category | Onboard 4 new clients | Max | 4 clients live | Contracts
65 | Week 9 | Dominate Category | Guest podcast #7: Contractor Success Forum | Rob | Episode recorded | Pitch
66 | Week 9 | Dominate Category | Ship second case study (T3 client ROI story) | Max | Case study live | Client data
67 | Week 9 | Dominate Category | Week 9 retro | Rob | Retro notes | —
68 | Week 10 | Dominate Category | Publish CloseClinic Certified Rep program ($497 one-time) | Max | Certification page live | Curriculum
69 | Week 10 | Dominate Category | Ship AI Rep Scorecard ($97/mo productized tool) | Max | Product live | Dev sprint
70 | Week 10 | Dominate Category | Close 4 more clients | Rob | 4 contracts signed | Pipeline
71 | Week 10 | Dominate Category | Onboard 4 new clients | Max | 4 clients live | Contracts
72 | Week 10 | Dominate Category | Publish State of Contractor Sales 2026 full report | Max | Report live + email blast | Survey data
73 | Week 10 | Dominate Category | Guest podcast #8: The Roofing Business Podcast | Rob | Episode recorded | Pitch
74 | Week 10 | Dominate Category | Week 10 retro | Rob | Retro notes | —
75 | Week 11 | Dominate Category | Pitch Inc., Fast Company, WSJ Pro (tier-1 press) | Max + PR | 3 pitches sent | Milestone data
76 | Week 11 | Dominate Category | Close 4 more clients | Rob | 4 contracts signed | Pipeline
77 | Week 11 | Dominate Category | Onboard 4 new clients | Max | 4 clients live | Contracts
78 | Week 11 | Dominate Category | Hire second FTE: Head of Sales | Rob | Offer extended | $100K MRR
79 | Week 11 | Dominate Category | Ship 3rd + 4th case studies (Tier 2 cohort) | Max | 2 case studies live | Client data
80 | Week 11 | Dominate Category | Guest podcast #9: Roofer Marketers | Rob | Episode recorded | Pitch
81 | Week 11 | Dominate Category | Week 11 retro | Rob | Retro notes | —
82 | Week 12 | Dominate Category | Close 4 more clients (approaching 30 total) | Rob | 4 contracts signed | Pipeline
83 | Week 12 | Dominate Category | Onboard 4 new clients | Max | 4 clients live | Contracts
84 | Week 12 | Dominate Category | Secure tier-1 press hit #1 (Inc. or Fast Company) | PR | Press placement confirmed | Pitches
85 | Week 12 | Dominate Category | Guest podcast #10: Construction Leading Edge | Rob | Episode recorded | Pitch
86 | Week 12 | Dominate Category | Publish Wikipedia entity draft (citation basket ready) | Max | Draft submitted | 20+ press hits
87 | Week 12 | Dominate Category | Week 12 retro + pipeline review | Rob | Retro notes | —
88 | Week 13 | Dominate Category | Ship 5th + 6th case studies; Success Stories refresh | Max | Page refreshed | Client data
89 | Week 13 | Dominate Category | Close 3 final clients — reach 30 active, ~$120K MRR | Rob | 3 contracts signed | Pipeline
90 | Week 13 | Dominate Category | DAY 90 MILESTONE: 30 clients, $120K MRR, 2 FTEs, tier-1 press | Rob | Milestone achieved | All prior tasks

## 3-Year Financial Projection
3-YEAR FINANCIAL PROJECTION
YEAR 1 (2026) — QUARTERLY
Metric | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Year 1 Total
Net New Clients | 5 | 15 | 30 | 50 | 100
Active Clients (ending) | 5 | 18 | 42 | 82 | 82
MRR (ending) | 17000 | 88000 | 220000 | 435000
Revenue (quarterly) | 30000 | 210000 | 540000 | 975000 | 1755000
COGS | 10000 | 65000 | 170000 | 310000 | 555000
Gross Profit | 20000 | 145000 | 370000 | 665000 | 1200000
GM% | 67% | 69% | 69% | 68% | 68%
OpEx (team, tools, mktg) | 25000 | 80000 | 175000 | 285000 | 565000
EBITDA | -5000 | 65000 | 195000 | 380000 | 635000
YEAR 2 (2027) + YEAR 3 (2028) — ANNUAL TARGETS
Metric | Year 2 Target | Year 3 Target
Active Clients | 220 | 450
MRR (December) | 1280000 | 2950000
Annual Revenue | 11200000 | 26500000
Gross Margin % | 70% | 72%
EBITDA | 4100000 | 11800000
Headcount | 18 | 42

## Unit Economics
UNIT ECONOMICS — TIER 2 (LEAKY BUCKET AI @ $4,997/MO)
REVENUE
Line Item | Monthly | Annual | 3-Year | Notes
Monthly Subscription | 4997 | 59964 | 179892 | $4,997/mo standard pricing
Onboarding Fee (1x) | 5000 | 5000 | 5000 | One-time at kickoff
TOTAL REVENUE |  |  |  | M1 revenue includes onboarding
COGS PER CLIENT
Line Item | Monthly | Annual | 3-Year | Notes
Voice minutes (1,200/mo @ $0.09) | 108 |  |  | Synthflow + Twilio blended
Synthflow agency plan (amortized) | 40 |  |  | $399/mo ÷ ~10 clients
Chatbase agency plan (amortized) | 50 |  |  | $500/mo ÷ ~10 clients
Twilio / A2P 10DLC | 5 |  |  | Phone number + registration
n8n self-hosted (infra share) | 2 |  |  | $20/mo Hetzner ÷ many clients
GHL sub-account | 10 |  |  | Rob's existing reseller plan
ElevenLabs voice upgrade | 22 |  |  | Premium voice for flagship clients
Buffer / overage | 25 |  |  | Over-usage minutes, tools
TOTAL COGS (infra only) |  |  |  | ~$262/mo infra only → ~95% gross margin on tech
Coach labor (4hr/mo @ ~$250/hr fully loaded) | 1000 |  |  | 1x weekly coaching call + async Slack
GROSS PROFIT & LTV
Metric | Monthly | Annual | 3-Year | Notes
Revenue (subscription only) |  |  |  | Excludes onboarding
Total COGS (infra + labor) |  |  |  | Infra + coach time
Gross Profit |  |  |  | Revenue minus COGS
Gross Margin % |  |  |  | Target 65-72%
LTV ASSUMPTIONS
Metric | Value |  |  | Notes
Avg client lifetime (months) | 24 |  |  | Target 24mo retention
Lifetime Revenue |  |  |  | Subscription x months + onboarding
Lifetime Gross Profit |  |  |  | Monthly GP x lifetime months
Assumed CAC | 1800 |  |  | Blended: content + sales time
LTV:CAC |  |  |  | Target 3:1 minimum, 5:1 healthy
CAC Payback (months) |  |  |  | Target < 6 months

## Tech Stack
TECH STACK — 12-Tool AI + Orchestration Layer
Layer | Tool | Monthly Cost | Why | Setup Time | Critical (Y/N)
Voice AI (primary) | Synthflow (agency plan) | $399 + $0.09/min | GHL-native, roofing templates, 2-3 day build | 2-3 days | Y
Voice AI (fallback) | Retell AI (power tier) | $200 + $0.11/min | Secondary voice provider for SLA redundancy | 1 day | Y
Chat AI | Chatbase Agency | $500 unlimited bots | White-label, fastest setup | Same day | Y
Orchestration | n8n self-hosted (Hetzner/Railway) | $20 | Rob already owns it, infinite operations | Half day | Y
Telephony | Twilio | $0.014/min + $5/number | A2P 10DLC compliance, number porting | 2 days | Y
CRM | GoHighLevel (sub-accounts per client) | Rob's existing plan | Zero additional cost, white-label ready | 1 day | Y
Website | Next.js on Vercel | $20 | Native build per Rob's rules, schema-first | 1 day | Y
Calendar | GHL native calendar | Included | Zero friction, client-facing booking | Same day | N
Voice premium | ElevenLabs Conversational AI | $0.08-0.15/min | Best voice quality for flagship clients | 2 hours | N
LLM (custom tier) | Anthropic Claude Sonnet 4.6 (caching) | ~$3/$15 per MT | 90% cache savings at scale | Ongoing | N
Analytics | PostHog | Free tier | Product analytics + session replay | 1 hour | N
Email / Transactional | Resend | $20 | Transactional, deliverability > Mailgun | 1 hour | N

## KPI Dashboard
KPI DASHBOARD — Weekly Tracker
Category | Metric | Target | Week 4 | Week 8 | Week 12 | Notes
Commercial | MRR | $120K by Day 90
Commercial | ARR | $1.44M by Day 90
Commercial | Net new MRR | $30-40K/month steady
Commercial | Logo churn | < 3%/mo
Commercial | Gross dollar retention | > 95%
Commercial | Net dollar retention | > 110%
Commercial | CAC | < $2,000 blended
Commercial | CAC payback period | < 6 months
Commercial | LTV | > $60K/client
Commercial | LTV:CAC | > 3:1 (target 5:1)
Commercial | Win rate (discovery → close) | > 30%
Commercial | Sales cycle length | < 21 days avg
Commercial | Upsell rate (T1 → T2) | > 40% in 90 days
Product / Delivery | Client NPS | > 70
Product / Delivery | Time to first-value | < 14 days
Product / Delivery | AI receptionist answer rate | > 95%
Product / Delivery | AI-to-appointment conversion | > 28%
Product / Delivery | Case studies shipped per quarter | ≥ 4
GEO / AI Visibility | AI citations per month | 25+ by Day 90
GEO / AI Visibility | Wikipedia submission readiness | Citation basket ≥ 20 tier-2
GEO / AI Visibility | Schema coverage (% of pages) | 100%
GEO / AI Visibility | llms.txt completeness score | 10/10
GEO / AI Visibility | Reddit mentions per month | 25+
GEO / AI Visibility | Press hits (tier 1 / 2 / trade) | 1 / 3 / 5 by Day 90

## Risk Register
RISK REGISTER
Risk | Probability | Impact | Mitigation | Owner | Status
STG claims non-compete or trade secret violation | Low | High | Retain employment attorney, document clean exit, avoid STG client poaching for 90 days | Rob
Synthflow outage brings down client receptionists | Medium | High | Fallback to Retell AI secondary, SLA credits to clients, 24/7 on-call during Year 1 | Max
AI voice regulation shifts (CA, CO, TX disclosures) | High | Medium | Bake disclosure prompts into every agent, monitor legal newsletters, audit quarterly | Max
Rob hires wrong FTE #1 (Head of Delivery) | Medium | High | Use STG-era network for vetted referrals, 90-day trial, clear scorecard, monthly check-ins | Rob
Early client churn kills momentum | Medium | High | Monthly NPS, escalation protocols, overdeliver for first 10 clients, personal Rob touchpoint | Rob + Delivery
Competitor copies the AI Receptionist positioning | High | Medium | Move fast, ship case studies, schema entity-grab, trademark 'Leaky Bucket Diagnostic', Wikipedia race | Rob + Max
Cash crunch before profitability | Low | High | Start with $100K cash reserves, Mercury credit line, no hiring before $50K MRR | Rob

## Name Shortlist
NAME SHORTLIST — Top 5 Candidates (all 3 TLDs available)
Rank | Name | Memorability (/10) | GEO Score (/10) | .com | .ai | .co
1 | CloseClinic | 9 | 9 | Available | Available | Available
2 | AceClose | 9 | 9 | Available | Available | Available
3 | HardHatSales | 9 | 8 | Available | Available | Available
4 | HomeRunRev | 8 | 8 | Available | Available | Available
5 | HammerClose | 8 | 8 | Available | Available | Available
RECOMMENDATION
PRIMARY: CloseClinic — the clinic/diagnostic metaphor extends through all 3 service tiers (Exam → Prescription → Treatment) and gives every piece of marketing content a native framework. BACKUP: AceClose — if CloseClinic feels too medical.